## Sheet1
Area | Group | Activity | Observation | Suggestion | Department | Name | Action | Open/ closed | Update
Accessible route | All | Security | Not easily identificable | Signage review | Ops | PS/DLM | CCD artwork on hold 08/10/19. KE to look at simpler artwork. Agreed 08/10/19 | Open | 21/01/2020 revision includes magenta block to highlight accessible deaprture route and assistance desk. CS/DLM discuss trail sunflower logo arrival route.
Accessible route | Sensory/mobility | Security | Preparing for search is stressful. Space at the head of the accessible route is available | Process review | Ops | DLM/CS | Capex has been applied for. Awaiting decision. If rejected can look to see what is available at end of year to supply something a little more basic that is acceptable to passengers. Agree in principal with the idea 12/12/19 | Open | Review suggestions by WJ colleagues to look at possible use of lane 1 which could also benefit families. Added bonus that it is away from FT pax stressing to rush through lane 7. 21/02/20
Accessible route | All | Security | Would floor decals help with access to and through security | Process review | Ops | DLM/CS | confusing to other pax if one decal for accessibility. Focus on signage at accessibility point | Closed
Arrivals Process | All except mobility | Pax journey | Stairs from eastern core most commonly used | Add hi vis step edging | Facilities | MR/CG | Referred to MR/CG 21/01/20 | Open | 2020-01-21
Arrivals Process | All except mobility | Pax journey | Number of steps to top not indicated | Signage review | Ops | PS/DLM | Included in draft proposal from CCD for departure route | Open | 2020-01-21
Arrivals Process | All | Pax journey | Distance along glass corridor and extenrnal walkway not indicated | Signage review | Ops | PS/DLM | Include in next phase of signage review | Open | 2020-01-21
Arrivals Process | All | Pax journey | Consider adding wheelchair stations and assistance call points | Process review | Ops | PS/DLM | Email to ABM to look at suggestion and trail period 21/02/20 | Open | 2020-02-21
Assistance desk | All | Assistance | Review signage on back wall which has Omniserv written large. | Replace with ‘Assisted travel;’ | Ops | PS/DLM | Discussion with Ominserve and ABM to agree not to replace Omniserve sign with the new ABM logo. CCD rebranding to focus more on accessibility generally. | Closed | 2019-12-02
Assistance desk | All | Assistance | High level blue signage above Assistance desk. It is above eye level and is missed | Signage review | Ops | PS/DLM | Included in draft proposal for CCD | Closed | 2020-01-21
Baggage reclaim | All | Pax journey | More seating required in the event of a baggage reclaim wait | Equipment review | Ops | DLM | 4 additional banks of seating moved into the BR area | Closed | 2020-01-07
Baggage reclaim | visual | Pax journey | Signage is poor with small unreadable fomts used | Signage review | Ops | PS/DLM |  | Open | 2020-01-21
Baggage reclaim | All | Pax journey | No help points if the bag facs desk is unmanned | Facilities review | Ops | PS/DLM |  | Open | 2020-01-21
Boarding Card check | All | Security | No directional information for wheelchair, families with strollers or general assistance | Signage review | Ops | PS/DLM | Agent in situ . Consider a wheelchair and buggy logo | Open | 2020-01-21
Boarding Card check | Hearing | Security | No hearing loop | Add portable hearing loop | Ops | PS/DLM | Meeting with Commercial to confirm numbers required for retail and f&b partners to progress order | Open | email to DT to confirm number required 21/01/20
Boarding Card check | All | Security | Security prep information prior to scan point has too much information to assimilate | Signage review | Ops | PS/DLM | No action to date 21/02/20 | Open | 2020-01-21
Boarding Process | Sensory/hidden | Boarding | Varied boarding expereince ( first or last ) to be clarified | Airline processes | Ops | CS | email to CB and NC to clarify 21/01/20 | Open | 2020-01-21
Boarding Process | All | Boarding | Distance indication and décor could be more passenger friendly | Signage review | Ops | PS/DLM | Is this included in CCD proposal? | Open | 2020-01-21
Boarding Process | Mobility | Boarding | Ambilft cleanliness not at an acceptable standard | PRM process | Ops | DLM/LO | Actioned by Omniserve immediatley confirmation of completion. | Closed | 2019-10-31
Bus stop | Visual | Access | Bus stop design and colours lack contrast | Add contrasting decals | Facilties | MR/CG | email to MR/CG 21/01/20 | Open | 2020-01-21
Call Points | All | Help | Yellow works well. Image & txt are small and hard to see | Add larger pictogram & txt | Car park | MR/CG | email to MR/CG 21/01/20 | Open | 2020-01-21
Call Points | Visual | Help | Image & txt are small & hard to see | Add tactile txt | Car park | MR/CG | email to MR/CG 21/01/20 | Open | 2020-01-21
Car Parks | Mobility | Vehicle Access | Not all disabilities need extra space to get in & out of vehicles | Add wheelchair only bays | Car park | SE | email of MR/CG to clarify if SE or not21/01/20 | Open | 2020-01-21
Car parks | Audio | Speaking to pax | We do not have hearing loops in the Car park office | Add a hearing loop | Car park | SE | email to SE to confirm order 21/02/20 | Open | 2020-01-21
Changing Place | Mobility | Pax journey | Phone needed to call for assistance | Equipment review | Facilities | MR/CG | Review carried out and no action required | Closed | 2019-10-31
Changing Place | Mobility | Pax journey | Instructions to use changing table, show and hoist needed | Equipment review | Facilities | MR/CG | Checked and instructions not in place at 21/01/20. Email to MR/CG | Open | 2020-01-21
Check in concourse | All | Assistance | Former assistance desk signage remains in place ( opposite easyjet check in ) | Remove | Facilities | BL/JL | Actioned October 2019 | Closed | 2019-10-31
Check in concourse | All | Pax journey | Departures signage is obscured by pillars at check in | Signage review | Ops | PS/DLM | Proposals for approval from CCD. Ongoing 21/01/20 | Open | 2020-01-21
Check in concourse | Visual | Pax journey | FID screens are difficult to see due height | Add lower level screens | Ops/IT | PS/DLM | Signage review. Ongoing 21/01/20 | Open | 2020-01-21
Check in concourse | Visual | Pax journey | Information point cube above FIDS is redundant | Relocate to assistance point | Facilities | BL/JL | Signage review. Ongoing 21/01/20 | Open | 2020-01-21
Check in concourse | All | Pax journey | High level blue wayfinding signage at FID point is not visible from west & east | Signage review | Ops | PS/DLM | Signage review. Ongoing 21/01/20 | Open | 2020-01-21
Check in concourse | All | Pax journey | Check in screens could be used for advice & greeting messaging | Signage review | Ops | PS/DLM | check in screens now upgraded, messaging and commecial advertsisng now live. | Closed | 2020-01-02
Check in concourse | All | Pax journey | Too much advertising content on check in screens. Image overload | Signage review | Ops | PS/DLM | revewed revently. Commercial considerations to consider. | Closed | 2020-01-02
Check in concourse | All | Pax journey | easyJet assistance check in is clearly identifiable at the Speedy boarding check in. | NAR |  |  | n/a | Closed | 2019-10-31
Check in concourse | All | Pax journey | Ryanair & other airline assistance check in is not identifiable | Review with airlines | OPS | DLM/CS | All airline logos will feature once chroa upgrade goes live Jan 20 | Open | 2020-01-02
Check in concourse | Hearing | Pax journey | Hearing loops located at assistance desk, FR & EZY check in. Staff lack knowledge | Information sharing with all | OPS | CS |  | Closed | 2019-10-31
Check in concourse | Hearing | Pax journey | Hearing loop serviceability not checked | Establish monthly checks | OPS | DLM/CS | Customer services walk up ad hoc checks in place | closed | 2019-10-31
Departure route | Sensory | Pax journey | No information on level 2 showing check in is down/ departures is up | Signage review | Ops | PS/DLM | The only way to L2 would have been to access from check-in area, departures signposted from entry points. | Closed | 2019-10-31
Departure route | Visual/sensory | Pax journey | Staircases are dimly lit = slip, trip & fall hazard | Lighting review | Facilities | BL/JL | Email to BL/JL 21/01/20 tp follow up on progress | Open | 2020-01-21
Departure route | Visual/sensory | Pax journey | Top and bottom stairs not clearly identificable | Add hi vis step edging | Facilities | MR/CG | Email to MR/CG 21/01/20 tp follow up on progress | Open
Departure route | Visual/sensory | Pax journey | Number of steps to top not indicated | Signage review | Ops | PS/DLM | Actioned, detail provided to CCD via DLM, signage agreed 08/10/19 | Closed | 2019-10-08
Departure route | Visual/sensory | Pax journey | Chrome & glass stair/escalator sides aren't clearly visible | Add decals/contrast -Signage review | Ops | PS/DLM | Email to signs express for progress update 21/1/20 ( also covers decals for galss arrival walkway between Kissing Gate and Surf box units in departures ) | Open | Order was never placed - conversation to be had with P St who had advised budget available
Departure route - lifts | All | Pax journey | Lifts from ground level to departures has low visibility signage | Signage review | Ops | PS/DLM | Actioned, addressed by CCD, signage agreed 08/10/19 | Closed | 2019-10-08
Departure route - lifts | Audio/visual | Pax journey | Tactile & audible emergency information not in place | Review with OTIS | Facilities | PS/DLM |  | Open
Departure route - lifts | All | Pax journey | Little information denoting what is on each floor in all lifts throughout terminal | Signage review | Ops | PS/DLM | Actioned, addressed by CCD, signage agreed 08/10/19 | Closed | 2019-10-08
Entrance | Visual/Sensory | Access | Dark rotunda door entance floor appears to be a chasm | Review flooring type | Facilties | MR/CG | Email to MR/CG 21/01/20 to follow up on progress | Open | 2020-01-21
Express Drop off | Mobility | Transit | Distance | Add distance/ number of steps | Facilties | MR/CG | Email to MR/CG 21/01/20 to follow up on progress | Open | 2020-01-21
Express Drop off | All | Load/unload | No information on how to get access foc period for Blue Badge holders | Review Process | Car park | SE | Email to SE 21/01/20 tp follow up on progress | Open | 2020-01-21
Gate 1- 10 | Mobility | Boarding | Pickerings lift is accessed on swipe only | Process review | Facilities | BL/JL | Reveiwed by DLM and DB, due to infastructire, collegues would need to approve use to prevent pax becoming stuck on lower level and no assistance to exit. | Closed | 2020-11-05
Landside directional signage | Visual | Pax journey | Signage is lacking when entering from the 'arrival' rotunda | Signage review | Ops | PS/DLM | Revewed and agreed new totem signage on two entry doors. Last 'arrival door' will be signposted as such to prevent entry for departured. | Closed | 2020-01-16
Landside directional signage | Visual/sensory | Pax journey | Signage near Subway faces central rotunda. Not visble if coming from the taxi rotunda. | Signage review | Ops | PS/DLM | Revewed and agreed new totem signage on two entry doors. Last 'arrival door' will be signposted as such to prevent entry for departured. | Closed | 2020-01-16
Landside directional signage | Visual/sensory | Pax journey | Lower level signage works better for some types of vision impairment | Signage review | Ops | PS/DLM | Revewed and agreed new totem signage on two entry doors. Last 'arrival door' will be signposted as such to prevent entry for departured. | Closed | 2020-01-16
Landside directional signage | Visual/sensory | Pax journey | No signage showing distance from taxi rank/arrivals door and assistance desk. | Signage review | Ops | PS/DLM | Was this covered by CCD? | Open | 2020-02-21
Landside directional signage | Visual/sensory | Pax journey | No 'You are here' terminal map options | Signage review | Ops/Comm | PS/DLM | Was this covered by CCD? | Open
Landside directional signage | All | Pax journey | Assistance desk - is there is insufficient indication for first time user? | Signage review | Ops | PS/DLM | Assistance desk has been identified as required by the wayfinding specialists. This has been approved. | Closed | 2020-01-16
Landside directional signage | All | Pax journey | Departures route signage as it is not visible when entering the arrival rotunda | Signage review | Ops | PS/DLM | Revewed and agreed new totem signage on two entry doors. Last 'arrival door' will be signposted as such to prevent entry for departures. Also lower level departures signage approved on the glass area. | Closed | 2020-01-16
Landside directional signage | All | Pax journey | Departures' route signage (central rotunda) not visible due to pillars and mezzanine level | Signage review | Ops | PS/DLM | Revewed and agreed new totem signage on two entry doors. Last 'arrival door' will be signposted as such to prevent entry for departures. Also lower level departures signage approved on the glass area. | Closed | 2020-01-16
Landside facilities | Mobility | Facilities | Payphones at arrivals and near to the Omniserv desk are too high for wheelchair users. | Discuss options with supplier | Commercial | DT/LO | DT provided data to show this is used minimally and not at all in Dec. Assistance desk team on hand to assist WCHR users | Closed | 2020-01-21
Landside facilities | All | Facilities | Directional signage to toilets which is missed and not visible to Starbucks users | Signage review | Ops | PS/DLM | New signage approved to clearly show toletets. | Closed | 2020-01-16
Main departures | Mobility | eat,drink, relax | Independent wheelchair users would like a locker facility to be able to eat/drink | Process review | Ops | DLM/CS | Reviewed. This presents some operational and security challenges and would not be agreeable unfortunatley. May need to look at options with airlines and check-in if this is a possibility to prevent such issues? | Closed | 2019-11-12
Main departures | Visual/sensory | eat,drink, relax | The zone signage appears to be moving | Signage review | Ops | DLM/CS | CCD artwork on hold 08/10/19. KE to look at simpler artwork. Agreed 08/10/19 | Closed
Main departures | sensory | eat,drink, relax | More directional information to the Picnic area | Signage review | Ops | DLM/CS | New signage agreed to move to 'family area'. | Closed | 2020-01-16
Passport control | All | Pax journey | Space is major issue | Facilities review | Facilities | MR/CG | Email to MR/CG 21/01/20 | Open | 2020-01-21
Roadway | All | Access | Kerbs not clearly identified | Add kerb markings | Facilties | MR/CG | Email to MR/CG 21/01/20 | Open | 2020-01-21
Route to terminal | All | Access | Tactile paving is limited | Add tactile paving route | Facilties | MR/CG | Email to MR/CG 21/01/20 | Open | 2020-01-21
Route to terminal | Visual | Access | Stainless steel posts where crossing meets terminal frontage | Add contrastind topper | Facilties | MR/CG | Email to MR/CG 21/01/20 | Open | 2020-01-21
Route to terminal | Visual | Access | White concrete bollards difficult to see | Add contrast colour | Facilties | MR/CG | Email to MR/CG 21/01/20 | Open | 2020-01-21
Route to terminal | Visual | Access | Crossing markings difficult to make out | Repaint | Facilties | MR/CG | Email to MR/CG 21/01/20 | Open | 2020-01-21
Route to terminal | All | Access | There is no clearly identifiable entrance | Review/replace entrance signage | Facilties | MR/CG | Actioned, addressed by CCD, signage agreed 08/10/19 | Closed
Security prep | Mobility | Security | High level prep table is too high for WCHR users. Vending is OK | Equipment review | Ops | SM/DLM | Table was approved as acessible via w/c. by CCD, also evidence of W/C pax using the table internally, picture availabke to evidence at 30/08/19 DLM | Closed
Security Screening | All | Security | Noise levels from trays, rollers and alarms make it difficult to hear instructions | Equipment review | Facilities | MR/CG |  | Open
Security Screening | Hearing | Security | Hearing loop on 2 of 7 lanes. In working order but staff not aware on how they work | Process review | Ops | DLM/CS | CS carrying out spot checks checking equipment and colleague knowledge | closed | 2019-10-31
Security Screening | All | Security | Information screens are not visble for Fast Track pax | Equipment review | Ops | MR/CG |  | Open
Security Screening | Mobility | Security | Wheelchair pax travelling independently find repack difficuly due to height of roller bed | Equipment review | Ops | PS/SM | Process review. WJ staff to intervene when help needed | Closed | 2020-01-21
Security search area | Visual/sensory | Security | Wave effect on arrow directing out of CSA appears as moving imagery | Signage review | Ops | CCD | Shared with CCD for planning further sgnage | closed | 2019-10-31
Taxi rank | Mobility | Transfer to vehicle | Change of level | Add ramp | Facilties | MR/CG | Email to MR/CG 21/01/20 to follow up on progress | Open | 2020-01-21
Taxi rank | Visualy | Transfer to vehicle | Kerbs | Add yellow kerb edging | Facilties | MR/CG | Email to MR/CG 21/01/20 to follow up on progress | Open | 2020-01-21
Upper retail area | Mobility | Retail | Self service W H Smith store has shelves which cannot be reached by wheelchair users | Commercial review | Commercial | DT/LO | DT has confirmed with WHS management that there will always be a member of staff in store to assist WCH users. He has asked for confirmation of WCHR accessible height option for self service check outs | closed | 2020-01-21
Upper retail area | All | Pax journey | Pax seen sitting beneath wayfinding screens waiting for gates to be displayed | Signage review | Ops | PS/DLM | No further issues reported | closed | 1900-01-20
Upper retail area | Sensory/medical | Pax journey | No independent access to rear corridor route for pax unable to pass through wdf | Process review | Ops | PS/DLM |  | Open | 1900-01-20
Upper retail area | All | Pax journey | The decorative illuminated red arrow ( part of F & B unit ) is confusing | Commercial review | Commercial | DT/LO | New signage to clearly denote access path through WDF to departures area. | Closed | 2020-01-16
Upper retail area | All | Pax journey | Signage 'to gate' pointing left through wdf under FIDs is easily missed | Signage review | Ops | PS/DLM | New signage to clearly denote access path through WDF to departures area. | Closed | 2020-01-16
Upper retail area | All | Pax journey | Signage to Prayer room & Quiet Space is missed | Signage review | Ops | MR/CG | Will form part of footprint works for Quiet Space | Closed | 2020-01-16
Upper retail area | All | Pax journey | Distance to gate information would be helpful | Signage review | Ops | PS/DLM | New signage to upgrade this sign approved. | Closed | 2020-01-16
Upper retail area | Visual | Pax journey | Top and bottom stairs not clearly identificable | Add hi vis step edging | Facilities | MR/CG | Email to MR/CG 21/01/20 tp follow up on progress | Open | 1900-01-20
Upper retail area | Visual | Pax journey | Decals on chrome and glass will help with visibility | Add decal -Signage review | Ops | PS/DLM | Email to PS/DLM 21/01/20 tp follow up on progress | Open | 1900-01-20
LAACC OCT19 Actions